## Assumptions
McCain Agentic Order Status — 3-Month Sprint Plan
Assumptions, scope and sources behind the sprint-by-sprint plan
Item | Value | Basis / note
Sprint length | 2 weeks | Matches the cadence already used in the Env/Services Requirements doc (Dev now, QA ~wk3, Prod ~wk5-6).
Sprint 1 start | Wed 29-Jul-2026 | Starts today, per your instruction.
Plan horizon | 6 sprints / 12 weeks (Jul 29 – Oct 20, 2026) | ~3 calendar months from today, per your request.
Team | 5-person StatusNeo forward-deployed engineering team | Per Env/Services Requirements doc, Section 8.
Scope | All 19 in-scope questions from "Full BOT Logic (Combined)" | Q1–Q19 in the OTC BOT Question Analysis workbook. Q21+ are explicitly marked "FUTURE QUESTIONS TO EXPLORE — NOT YET BUILT" in that sheet and are excluded.
Complexity scoring | Proxy = number of field/logic rows + SAP table joins + answer-scenario count per question, as documented in the workbook | Used only to sequence and balance sprints — not a formal estimate.
Duplicate / phrasing-variant questions | Q13 ≈ Q1, Q12 ≈ Q10, Q18 ≈ Q3, Q19 ≈ Q4 | Flagged as duplicates directly in the "Full BOT Logic (Combined)" sheet's question text. Built together with their parent question as one query template + NLU routing tests, not as separate engineering effort — this is why they land in the same sprint as their parent below.
Cross-team dependency flagged | Q5 (pallet-compliance) needs a calculated field that the workbook notes "exists on the supply chain BOT" | Recommend confirming ownership/reuse of that field by Sprint 3, even though the McCain build lands in Sprint 5, to avoid a late-discovered blocker.
Not covered by this plan | Region, peak concurrency/volume, QA vs UAT merge, cost ceilings | Still open decisions from Amit per Section 11 of the requirements doc — sizing and this schedule may shift once confirmed.
QA environment ownership | Owned by a separate McCain QA/platform team — not the StatusNeo build team | Not tracked as a milestone in this plan. Our team keeps building and running the evaluation gate (golden-set: 22 functional + 22 security tests) in Dev regardless of which environment is available; features promote to QA/Prod on that team's timeline.
Sprint 1 detail | See the "Sprint 1 Detail" tab | Real task-by-task breakdown supplied by the team (11 tasks, U1-01 to U1-11) — Sprint 1 is the full flagship Order Status build (RBAC, DB Shield, all 8 order states, disambiguation, follow-ups, guardrails, tracing, evaluation gate, UI prototype, bug-bash & demo dry-run), not a setup-only sprint.

## Sprint Summary
Sprint Summary — 3-Month Plan (Jul 29 – Oct 20, 2026)
6 x 2-week sprints. "Questions delivered" count is pulled live from the Question Backlog tab.
Sprint | Dates | Platform / environment milestone | Bot-logic focus (theme) | Questions delivered this sprint | # Questions | Exit criteria
Sprint 1 | 29-Jul – 11-Aug 2026 | Dev environment already provisioned by McCain (not our task). Week 1 opens by confirming access + EDP table readability (U1-01), then our team builds RBAC/Unity Catalog scope (U1-02), DB Shield (U1-04), Prompt Shield + output guardrails (U1-08), and tracing + the evaluation gate (U1-10) directly on top of it. Full day-by-day breakdown on the "Sprint 1 Detail" tab. | Flagship: full Order Status build (not just setup) — see Sprint 1 Detail tab | Q1, Q13 | 2 | Full E01–E22 functional + SEC-01–22 security evaluation set run and passing, no criticals (U1-10); team bug-bash complete, demo dry-run clean, go/no-go called for the 2-week milestone (U1-11).
Sprint 2 | 12-Aug – 25-Aug 2026 | No environment-enablement work on our critical path this sprint. QA stand-up and ownership sits with a separate McCain QA/platform team — it is not tracked as our milestone. We keep building and running the evaluation gate in Dev; features promote to QA/Prod whenever that team makes it available. | Order scheduling & holds | Q4, Q19, Q14, Q10, Q12 | 5 | 5 questions built and passing the golden-set evaluation gate in Dev; ready to promote once QA is available.
Sprint 3 | 26-Aug – 08-Sep 2026 | Prod environment enablement targeted around this time by McCain's platform team (per Requirements doc §1) — their milestone, not ours. Once it's available: controlled soft launch + stakeholder demo. | Shortages & fill-rate analytics | Q3, Q18, Q9, Q6 | 4 | Q1/Q13 ready to promote to Prod for the stakeholder demo as soon as the environment is handed over; shortage/fill-rate cluster passing the evaluation gate in Dev.
Sprint 4 | 09-Sep – 22-Sep 2026 | Promote Sprint 2–3 clusters to Prod after soak; begin Inventory (Fact.IM_Inventory_Balance) domain. | Inventory, customer history & shortage ranking | Q2, Q7, Q17 | 3 | Inventory domain online; full shortage/fill-rate analytics set (Q3,Q6,Q9,Q17,Q18) complete and in Prod.
Sprint 5 | 23-Sep – 06-Oct 2026 | Confirm shared calculated field with the Supply Chain BOT team for Q5 before build starts. | Packaging/pallet compliance & billing | Q5, Q15, Q16, Q8, Q11 | 5 | Packaging and billing (Fact.Sellin) domains online; all 19 questions functionally complete across environments.
Sprint 6 | 07-Oct – 20-Oct 2026 | Full 19-question regression run wherever QA/Prod are available by then; performance & load testing; security review of Prompt Shield/DB Shield; documentation & handover; go-live readiness review with Amit. | Hardening & go-live (no net-new questions) | (regression/buffer only) | 0 | All 19 questions live in Prod, evaluation gate green, sign-off for full production rollout.
Total |  |  |  |  | 19

## Sprint 1 Detail
Sprint 1 Detail — Week 1-2, as scoped by the team
Verbatim task breakdown. Sr = Senior, Fr = Fresher/junior. "X (Sr)" is a to-be-confirmed senior hire on the roster.
Week | Days | ID | What we're doing | Steps (plain English) | How we know it's done (acceptance) | Covers (eval IDs) | Owner
Week 1 | 1-2 | U1-01 | Confirm readiness, data & rules | 1) Confirm env + tool access for everyone. 2) Confirm we can read the EDP order/delivery/shipment/billing tables. 3) Seed the Genie space with these tables + clear column descriptions. 4) Re-confirm the 8-state answer logic, follow-ups and business rules are signed off. | AC1: Team can build; EDP tables readable. AC2: Genie answers a couple of sample order questions. AC3: Answer logic + follow-ups confirmed in writing. | — | Alok + Prateek (Sr)
Week 1 | 1-3 | U1-02 | Set up who-can-see-what (RBAC scope) | 1) Register the order tables in Unity Catalog. 2) Add the row filter so a user only sees their sales org/region. 3) Add column masks for restricted fields (pricing, margin, cost, personal data). 4) Give the agent its own read-only, least-privilege login. | AC1: A test user only sees their sales org. AC2: Masked fields hidden. AC3: Agent identity is read-only, least-privilege. | SEC-01/02/03/04/05/16 | Shivansh (Fr, rev: Prateek)
Week 1 | 2-4 | U1-03 | Agent core — understand the question | 1) Detect the 'order status' intent and politely decline out-of-scope. 2) Pull out the details (order/PO number, SKU, customer, dates) with typo/synonym handling. 3) Ask to confirm when a value is ambiguous. | AC1: Intent + details correct on the test questions. AC2: Out-of-scope handled. AC3: Ambiguous input asks to confirm. | E14, E21, E22 | Prateek (Sr)
Week 1 | 2-5 | U1-04 | Order lookup tool + DB Shield | 1) Build the Genie tool that turns the question into read-only SQL over the order tables and returns the answer + the SQL. 2) Add the DB Shield: SELECT-only, allowed tables, LIMIT, timeout, least-privilege login. 3) Block and log anything unsafe. | AC1: Real order questions answered from data with SQL shown. AC2: Unsafe/changing SQL blocked (tested). AC3: Runs read-only. | SEC-12/13 | X (Sr)
Week 1 | 3-5 | U1-05 | The 8 order states + freshness + not-found | 1) Turn raw data into the correct status: Cancelled, Blocked (credit/delivery/billing), Open, Delivery created, Shipment created, Shipped-not-billed, Complete, Not found. 2) Grounded, cited reply per state with the right date. 3) Show 'data as of' + 2-hour note. 4) Handle not-found and multiple matches. | AC1: Each of the 8 states returns the correct reply from data. AC2: Freshness shown. AC3: Not-found/multi-match handled. | E01-E10, E12 | X (Sr, pair: Madhavan)
Both | 1-8 | U1-09 | UI prototype + approval (Syed's sprint task) | 1) Build a clickable prototype of the chat screen like MCX (question, grounded answer, order card, 'View SQL' source, 'data as of') AND the observability/evaluation dashboard views (KPI tiles + E/SEC pass-fail). 2) Review with the product owner / CS and stakeholders; capture feedback and iterate. 3) Get sign-off on the look-and-feel and key flows. 4) STRETCH (if time permits): start wiring real functionality to the agent backend. | AC1: Clickable prototype of the chat + dashboard exists. AC2: Reviewed with stakeholders; feedback captured. AC3: Sign-off on look-and-feel & flows obtained. AC4 (stretch): initial functionality wired if time allows. | UI/UX (design) | Syed (Sr, full-stack) + Madhavan (Fr)
Week 2 | 6-7 | U1-06 | Disambiguation flows | 1) PO matching >1 order -> ask which order/plant/ship-to. 2) >1 delivery on an order -> ask which delivery. 3) Order/PO not found -> offer a name-based lookup. 4) No identifier -> ask for the order or PO. | AC1: Each disambiguation flow asks the right question then answers. AC2: No guessing. | E11, E12, E13, E14 | X (Sr)
Week 2 | 6-7 | U1-07 | Follow-up questions (multi-turn) | 1) Keep context on the same order. 2) Answer: 'when will it ship?', 'why is it blocked / who releases it?', 'invoice number & date?', 'which delivery/shipment?'. 3) Handle the 'list not-shipped by product' phrasing. | AC1: Follow-ups answered from the earlier order context. AC2: Alt 'list' phrasing works. | E15, E17, E18, E19 | Prateek (Sr)
Week 2 | 6-8 | U1-08 | Guardrails & security (corner cases) | 1) Prompt Shield for jailbreaks + injected instructions (including instructions hidden in order data). 2) Output checks: answer only from data + cite, redact personal data, 'not permitted for your role' message for restricted fields. 3) Scope enforced from the login, never from chat. 4) Handle empty/huge/abusive/off-topic input. | AC1: Jailbreak/injection refused, still helpful. AC2: Restricted fields give a proper message, no leak. AC3: Out-of-scope always 'not found'. | SEC-06-11, SEC-15, SEC-17-22 | Shivansh (Fr) + X (Sr, rev: Prateek)
Week 2 | 8-9 | U1-10 | Tracing + run the evaluation gate | 1) Turn on tracing (route, SQL, tokens, latency, cost), no PII in logs, and expose the metrics the dashboard will need. 2) Run the full evaluation set: 22 functional (E01-E22) + 22 security/corner (SEC-01-22). 3) Record pass/fail + a short quality report. | AC1: Every run traced (no PII); metrics available. AC2: E-set + SEC-set run and scored. AC3: Pass/fail report exists. | All E + all SEC | Prateek (Sr)
Week 2 | 9-10 | U1-11 | Fix, bug-bash & demo dry-run | 1) Fix evaluation failures and obvious bugs. 2) Whole-team bug-bash on real (scoped) test orders. 3) Dry-run the demo (with the approved prototype + working backend). 4) Go / no-go for the 2-week milestone. | AC1: Evaluation passes (no critical failures). AC2: Demo dry-run clean. AC3: Go/no-go agreed. | All E + all SEC | Whole team

## Question Backlog
Question Backlog — all 19 in-scope questions
Source: "Full BOT Logic (Combined)" + "EDP Tables", OTC_BOT_Question_Analysis workbook. Complexity tier is a sizing proxy (field/logic rows, SAP joins, answer-scenario count), not a formal estimate.
Sprint | Q# | Question | Theme | Primary EDP fact / SAP tables | Pairing / duplicate note | Complexity | Status
Sprint 1 | Q1 | What is the status of order 123? (by SAP order # or PO #) | Order status / lookup | Fact.SalesOrder (VBAK/VBAP/VBUK/VBEP/VBKD) | Flagship capability — anchors the whole build. | High | In progress
Sprint 1 | Q13 | Give me a list of all orders with product xxx that have not shipped yet. | Order status / lookup | Fact.SalesOrder (VBAK/VBAP/VBUK) | Alternate phrasing of Q1, noted in the workbook itself — build as one NLU route + query template with Q1. | Medium | In progress
Sprint 2 | Q4 | List past-due CPU orders (planned PGI date in the past, not yet PGI'd), for [sales org], [time frame]. | Past-due / loading schedule | Fact.SalesOrder + Fact.Delivery (VBEP/VBUK/VBAK) | Parent of Q19 — build together. | Medium | Not started
Sprint 2 | Q19 | Which orders had a planned loading (PGI) date in the past but have not yet loaded, for [sales org], [time frame]? | Past-due / loading schedule | Fact.SalesOrder + Fact.Delivery (VBEP/VBUK/VBAK) | Workbook flags this as "duplicated, same as question 4" — same query template as Q4, ship as an NLU regression variant, not new logic. | Medium | Not started
Sprint 2 | Q14 | Give me a list of orders that have an estimated loading date (planned PGI date) of [date/date range]. | Loading schedule | Fact.SalesOrder (VBEP) | Forward-looking counterpart to Q4/Q19 (future date vs. past-due) — distinct, not a duplicate. | Low | Not started
Sprint 2 | Q10 | List orders scheduled to load in the next 2 days that are currently on credit/delivery/billing hold. | Credit management + loading schedule | Fact.SalesOrder (VBUK-CMGST/VBEP) | Parent of Q12 — build together. | Low | Not started
Sprint 2 | Q12 | List orders past their planned loading date that are on delivery block, for [sales org], [plant/WH], [time frame]. | Delivery blocks | Fact.SalesOrder (LIKP/VBEP) | Workbook flags this as "duplicated from question 10" — same block-check logic as Q10, ship as a variant. | High | Not started
Sprint 3 | Q3 | Show orders with delivery created but confirmed qty < ordered qty (shortages), not yet shipped, for [sales org]/[date range]. | Delivery vs. ordered qty (shortages) | Fact.SalesOrder + Fact.Delivery (LIKP/LIPS/VBAP) | Parent of Q18 — build together. | Medium | Not started
Sprint 3 | Q18 | Which products currently have shortages (confirmed qty < ordered qty), for [sales org], [time period]? | Delivery vs. ordered qty (shortages) | Fact.SalesOrder + Fact.Delivery (VBAP/LIPS) | Workbook flags this as "duplicated, same as question 3" — same shortage logic as Q3, ship as a variant. | High | Not started
Sprint 3 | Q9 | List orders fully confirmed at delivery-note creation but shipped less than the confirmed quantity. | Delivery vs. ordered qty (shortages) | Fact.SalesOrder + Fact.Delivery + Fact.Shipment (LIPS) | Distinct scenario from Q3/Q18 — checks confirmed-vs-shipped, not confirmed-vs-ordered. | Low | Not started
Sprint 3 | Q6 | What is the fill rate for customer [XX] at plant [XXXX] for [time frame]? | Fill rate & shortage analytics | Fact.SalesOrder (VBAK/VBAP/LIKP/LIPS) | Aggregation on top of the shortage tables built this sprint. | Medium | Not started
Sprint 4 | Q2 | What is the current on-hand stock (in cases) for SKU [123] at plant [xxxx], and how many open orders exist against it? | Inventory / stock | Fact.IM_Inventory_Balance + Fact.SalesOrder (MARD/MCHB) | New data domain (inventory) — first use of this fact table. | Medium | Not started
Sprint 4 | Q7 | List products purchased by customer [XXXX] and the producing plant for each, for [time frame]. | Customer purchase history | Fact.SalesOrder + DimMaterialBatch (KNA1/KUAGV) | Plant determination depends on batch ID — confirm mapping with EDP team. | Medium | Not started
Sprint 4 | Q17 | Which customers are most impacted by shortages (rank by qty/value), for [sales org], [time period]? | Fill rate & shortage analytics | Fact.SalesOrder (aggregated) | Ranking/aggregation built on the Q3/Q6/Q18 shortage logic from Sprint 3. | Low | Not started
Sprint 5 | Q5 | For plant xx, list orders where SKUs are not ordered in full pallet quantities. | Packaging / pallet compliance | Fact.SalesOrder + DimFullPalletCustomerConversion (MARA/MARM) | Needs a calculated field the workbook notes "exists on the supply chain BOT" — confirm reuse/ownership by Sprint 3 to avoid a late blocker. | Low | Not started
Sprint 5 | Q15 | What are the cases-per-pallet, gross weight, net weight, and EAN/UPC for SKU [XXXX]? | Packaging / pallet compliance | DimProduct + DimProductConversionFactors (MARA/MARM) | Master-data lookup only — lowest-risk item in the plan. | Low | Not started
Sprint 5 | Q16 | List open orders with pallets, cases, and weight, for customer [ID/Name] in [sales org]. | Packaging / pallet compliance | Fact.SalesOrder (VBAP/MARA/MARM) | Reuses Q15's packaging conversion logic. | Medium | Not started
Sprint 5 | Q8 | Show me orders that have been shipped but not yet billed, for [sales org], [time period]. | Billing / invoicing | Fact.SalesOrder (LIKP/VBRK/VBRP) | New data domain (billing) — first use of Fact.Sellin-adjacent billing tables. | Low | Not started
Sprint 5 | Q11 | List orders billed yesterday (dynamic date/time frame). | Billing / invoicing | Fact.Sellin (VBRK/VBRP) | Shares billing tables with Q8 — build together. | Low | Not started