## Slide 1
AGENTIC ORDER STATUS ENQUIRY ASSISTANT
Design, Architecture, Timeline & Status
Prepared for Manoj — CTO, McCain
StatusNeo — Forward Deployed Engineering | 29 July 2026

## Slide 2
AGENDA
What we'll cover
1
Solution scope
19 questions across 6 real CS-agent workflows
2
Architecture
A Databricks-native, defense-in-depth design
3
Delivery timeline
6 sprints, 3 months — 29 Jul to 20 Oct
4
Current status
Day 1 of Sprint 1, today
5
Decisions needed
What we need from McCain to size Prod
2
McCain · Agentic Order Status

## Slide 3
SOLUTION SCOPE
19 questions, 6 domains — sourced from real CS-agent workflows
2
Order Status & Lookup
“What's the status of order 123?”
5
Scheduling & Holds
Past-due, credit/delivery blocks, loading dates
4
Shortages & Fill-Rate
Confirmed vs. ordered/shipped quantity gaps
3
Inventory & Customer History
On-hand stock, what a customer's ordered before
3
Packaging & Compliance
Pallet, weight & UOM specs
2
Billing & Invoicing
Shipped-not-billed, billed-yesterday
3
McCain · Agentic Order Status

## Slide 4
ARCHITECTURE
Defense-in-depth, Databricks-native architecture
Azure
Databricks
SAP
1
User &
Sign-in
Entra ID SSO
→
2
API
Gateway
Rate limits, WAF
→
3
Prompt
Shield
Jailbreak defense
→
4
Agent
Model Serving
→
5
Genie +
DB Shield
Read-only SQL
→
6
Governed
Data
Unity Catalog
→
7
Output
Guardrails
Cited, redacted
SECURITY
SSO/SCIM · Private Link · read-only SQL
RESILIENCE
Autoscale · warm mins · graceful fallbacks
GOVERNANCE
Row/column security · lineage · audit
OBSERVABILITY
MLflow tracing · 44-test eval gate
Applied to every request, in every environment — a failure at one layer is contained by the next.
Dev → QA → Prod
Isolated Unity Catalog catalogs, promoted via Databricks Asset Bundles
EDP on ADLS Gen2
~2h refresh from SAP, read-only — SAP itself is never written to
Evaluation-gated
22 functional + 22 security tests must pass before any release
4
McCain · Agentic Order Status

## Slide 5
DESIGN PRINCIPLES
Built to be safe, governed, and observable by default
1
Guardrails at every hop
Prompt Shield, DB Shield (read-only SQL only) and output guardrails — a bypass at one layer is contained by the next.
2
Governed data access
Unity Catalog enforces row-level security by sales org and masks restricted fields (pricing, margin, PII) — never left to app logic.
3
Databricks-native
Genie for NL→SQL, Model Serving for orchestration — no unnecessary third-party layers between the agent and governed data.
4
Evaluation-gated releases
Every release is scored against a 44-test golden set (22 functional + 22 security) before it ships — no exceptions.
5
McCain · Agentic Order Status

## Slide 6
DELIVERY TIMELINE
3-month delivery plan — 6 sprints, 29 Jul → 20 Oct 2026
TODAY
Sprint 1
29 Jul – 11 Aug
Order Status flagship
Sprint 2
12 – 25 Aug
Scheduling & holds
Sprint 3
26 Aug – 8 Sep
Shortages & fill-rate + demo
Sprint 4
9 – 22 Sep
Inventory & customer history
Sprint 5
23 Sep – 6 Oct
Packaging & billing
Sprint 6
7 – 20 Oct
Hardening & go-live
Sprint 1 starts today. Sprint 6 ends with all 19 questions live and evaluation-gated in Prod.
6
McCain · Agentic Order Status

## Slide 7
CURRENT STATUS
Where we are today — Day 1 of Sprint 1
DONE
Requirements & environment (Dev/QA/Prod) plan finalized
Reference architecture defined — defense-in-depth, Databricks-native
3-month, 6-sprint delivery plan finalized
Sprint 1 backlog scoped in detail — 11 tasks, owners assigned
22 open questions identified for McCain & internal product team
IN PROGRESS — SPRINT 1
Order Status flagship build
RBAC & Unity Catalog scope · DB Shield · all 8 order states · disambiguation & follow-ups · guardrails · tracing & evaluation gate · UI prototype
Target: working demo + evaluation gate passed by 11 Aug
UPCOMING
Scale/region decisions from McCain — gate Prod sizing (next slide)
QA environment stand-up — owned by McCain's platform team
7
McCain · Agentic Order Status

## Slide 8
DECISIONS NEEDED
Decisions we need from McCain to size Prod correctly
1
Region & sequencing
Which regions/countries, and rolled out all at once or phased?
2
Users & peak concurrency
How many CS agents per region, and expected peak concurrent usage?
3
Single- vs. multi-region
Is one Azure/Databricks deployment enough, or does latency/compliance need more?
4
Landing zone alignment
Target region(s) and McCain's naming/landing-zone conventions
Full list of 22 open questions (client + internal product team) shared separately with Amit's team.
8
McCain · Agentic Order Status

## Slide 9
NEXT STEPS
What happens next
1
Finish Sprint 1
Complete the Order Status flagship build and pass the 44-test evaluation gate by 11 Aug.
2
Internal demo
Walk through the working Order Status assistant — all 8 order states, guardrails and citations.
3
Close open decisions
Get scale/region answers from McCain — needed before Sprint 3 Prod sizing.
4
Start Sprint 2
Scheduling & holds cluster begins 12 Aug, on the same 2-week cadence.
9
McCain · Agentic Order Status

## Slide 10
Thank you
Questions & discussion
Alok Ranjan
StatusNeo — Forward Deployed Engineering